WORK INSTRUCTION

FIELD EXTRA WORK ORDERS (SFR-FEWO)

INDEX

1.-	OBJECT	2

2.-	DEFINITIONS	2

3.-	DEVELOPMENT ACTIVITIES / DETAILED SCOPE	3

4.-	F.E.W.O. Evaluation methods	4

5.-	ATTACHMENT	4

-	SUBCONTRATOR FEWO REQUEST (SFR)	4

-	FIELD EXTRA WORK ORDER (F.E.W.O.)	4

- OBJECT

The present document establishes and defines the criteria for the control, cost calculation and payment of work variations (extra work) through Field Extra Work Orders (F.E.W.O)

- DEFINITIONS

CONTRACTOR: INTECSA / INITEC

SUBCONTRACTOR: company awarded by CONTRACTOR for the execution of the Construction, Pre-commissioning and Commissioning Project activities as defined within his scope of Works.

SUBCONTRACT: The Agreement and amendments with all annexes and appendices attached thereto, in which the relationship between CONTRACTOR and SUBCONTRACTOR to perform the awarded works is defined.

MODIFICATIONS or CHANGES: Variations that affect to the original scope of work which may cause an adjustment in the SUBCONTRACT’s price.

Modifications will be considered as additional works only when it may be clearly demonstrated that they have not been previously included and foreseen in the SUBCONTRACTOR´s Scope of Work.

Remark: All works which have to be done in order to rectify/correct/repair SUBCONTRACTOR´s defectives work will be solely SUBCONTRACTOR´s liability, therefore such cost shall not be borne by CONTRACTOR, thus they will not be considered as a FEWO.

SUBCONTRACTOR FIELD EXTRA WORK ORDER REQUEST (SFR): initial document issued by SUBCONTRACTOR in order to initiate the FEWO process for CHANGES if relevant.

Mentioned document consist of:

- Reference number: it shall be followed a sequential numbers starting from 000. SUBCONTRACTOR will request CONTRATOR in advance a number assignment prior processing and submitting the SFR. For the sake of clarity, number assignment does not stand for CONTRACTOR acknowledgement of SUBCONTRACTOR entitlement to be compensated

- Work description.

- Method of evaluation.

- Initial estimated cost.

- Estimated duration of the works.

- Related Technical documentation shall be attached: drawing revision, Technical Query, ETI,

etc.

- CONTRACTOR correspondence: TTL number, communication, whatever.

- Any other supportive documentation that may be required to enable CONTRACTOR to duly evaluate SUBCONTRACTOR cost calculation proposal. CONTRACTOR will reserve his rights to request further information if required.

On normal basis SUBCONTRATOR will provide an estimation of measurement, elemental operations, manpower, auxiliary means, materials required or any other needful information. The SFR shall be submitted through official communication and independently in order PARTIES keep a suitable traceability.

FEWOs shall be initiated by means of SFR, besides numbering will be maintained even for those cases by which SFR has not been accepted by CONTRACTOR, for such cases rejected FEWO will be recorded with null value.

FIELD EXTRA WORK ORDER (FEWO):

Document which closure the SFR, it is to say this document will contain all information previously stated within the SFR expect from cases where final quantities have varied according to the final Works measurement if relevant.

FEWO shall be issued when the works have been fully achieved and CONTRACTOR has successfully validated such Work, thus FEWO value will be the final and no the estimated except from LUMPSUM Prices. Once FEWO is approved SUBCONTRACTOR shall be deemed as fully compensated for executed work, therefore no further claims will be accepted for Works already foreseen in the SFR and afterwards closed within the FEWO.

In case of variation, the method of evaluation and the final cost are to be included together with a detailed breakdown of the measurement, elemental operations, manpower, equipment, materials or any other required additional information for describing the work.

FEWOs shall be submitted by official communication and shall be numbered accordingly (same number as corresponding SFR).

- DEVELOPMENT ACTIVITIES / DETAILED SCOPE

No additional / extra work shall be executed by SUBCONTRACTOR until corresponding SFR has been agreed and signed by PARTIES as stated in this document unless otherwise expressly stated by CONTRACTOR.

Only in the exceptional cases when there is no agreement in any of the terms of the SFR, the CONTRACTOR may give written instruction to SUBCONTRACTOR to proceed with such Works, pending resolution of such disagreement, which will be registered as an outstanding item to be resolved.

Any scope of work variation will be supported by filling the document named “Field Extra Work Order (F.E.W.O)” (Attachment Field Extra Work Order (FEWO) Form).

- F.E.W.O. Evaluation methods

The Evaluation Criteria necessary for the management and issuance of F.E.W.Os is below explained in detail. Besides SUBCONTRACTOR shall consider such prevalence for SFR/FEWO processing. It is to say; In case that Works may be evaluated by Subcontract Unit Prices other options will be rejected and so on.

  - Unit Prices

  - Elemental Operation Prioces.

  - New additional Prices.

  - Lump Sum Prices

- Measurement work and unit prices

This method is based on measurement and BOQ unit prices. Once works have measured unit prices will be applied. F.E.W.O will be issued as “MEASURED WORK”.

- Elemental Operation Prices

As per normal operation to be performed at Construction field: such as welding, beveling, cutting.. Elemental Operation Prices will be calculated by decomposing existing ones if no foreseen within SUBCONTRACT

- New additional prices which are not included within BOQ.

Supplement or additional Prices are related to items which have not been included in the BOQ/SUBCONTRACT, however may be calculated by prorating existing ones.

In case not to have such reference in the SUBCONTRACT, PARTIES will evaluate it taking into consideration other references as local market, etc.

- Lump sum works

“LUMP SUM” will be considered as valid when PARTIES agree for closing extraworks with an initial estimated Price regardless of final amounts involved.

- ATTACHMENT

- SUBCONTRATOR FEWO REQUEST (SFR)

- FIELD EXTRA WORK ORDER (F.E.W.O)