| RLLP | OMP/DGB | FAB | 02 | Nov 21 | General review |
| --- | --- | --- | --- | --- | --- |
| RLLP | OMP/DGB | CUP | 01 | Jun 20 | Issuance |
| APPROV. | VERIF. | PREP. | EDITION | DATE | DESCRIPTION |

FIELD PROCUREMENT PROCEDURE

INDEX

1.	PURPOSE AND SCOPE	3

2.	DEFINITIONS	3

3.	RESPONSIBILITIES	4

4.	FIELD PROCUREMENT SERVICES	5

5.	FIELD PROCUREMENT PROCEDURE	6

6.	PROCUREMENT CYCLE	6

6.1.	FOR MATERIAL	6

6.2.	FOR LOCAL SERVICES	9

6.3.	FOR SITE OFFICE MATERIAL	9

Attachment I – LOCAL PROCUREMENT FLOWCHART	10

- PURPOSE AND SCOPE

The purpose of this document is to provide a Field Procurement Procedure for the procurement services required by site for small amounts purchases and/ or urgent needs (Materials, services, and Site Office Material).

- DEFINITIONS

- AGREEMENT: means the legal binding agreement between CLIENT and CONTRACTOR.

- CLIENT: means the entity awarding the Contract to CONTRACTOR.

- CONTRACTOR: means INTECSA INDUSTRIAL or INITEC ENERGIA.

- BUYER: means the person designated by the Procurement Department Manager, who can be located in Madrid headquarters, in the local offices or at SITE.

- GOODS: means things of all kinds (other than Plant) intended to form or forming part of the Permanent Works, including supply MATERIALS/equipment & VENDOR Services to be supplied by the CONTRACTOR under the AGREEMENT.

- LOCAL MATERIAL REQUESITION (LMR): means the Contract’s document which defines the quantities and technical characteristics of each MATERIAL needed at SITE.

- PURCHASE ORDER (PO): means the legal binding AGREEMENT between CONTRACTOR and VENDOR for the provision of supplies related to the Contract, issued in the name of CONTRACTOR or the CLIENT.

- REQUEST FOR QUOTATION (RFQ): means the document issued by CONTRACTOR to SUPPLIERS for obtaining quotation for MATERIALS/services related to the Contract requirements.

- SITE: means the area where the Plant is to be built.

- VENDOR / SUPPLIER: means the Company appointed to supply any part of the Contract.

- SUB-VENDOR / SUB-SUPPLIER: The entity receiving the VENDOR’s order for supplying any part of the PURCHASE ORDER.

- MATERIAL: any supply that it is requested for the project (for example: piping, cables, spares, instrumentation, etc.).

- LOCAL SERVICES: any service that it is required at SITE (for example: car rental, mobile phone service, security service, bus service, power supply, generators, cranes, etc.)

- SITE OFFICE MATERIAL: any MATERIAL that it is required for Site Offices (for example: laptops, computers, printing services, consumables, gloves, PPEs, tools, etc.)

- RESPONSIBILITIES

- Project Procurement Manager (PPM): Approval all local procurement process.

- Procurement Department Manager: Approval and signing of orders.

- Project Manager (PM): Approval of commercial proposal comparison sheets/awards and signing of orders.

- Site Manager: Asks for requests for quotation to be sent out through the BUYER, approval of bidders and LMR and approval of commercial proposal comparison sheets/awards.

- Site Technical Office Manager: Defines the technical Scope of the Request For Quotation and completes the LMR. Also, is in charge of keeping the LMRs Log updated, using the standard format MI-45 Local Material Requisitions (LMRs) Log. If Site Technical Office Manager has not been assigned to the project, Site Manager and Project Manager shall designate which Manager at site shall follow the procedure and issue each LMR.

- Buyer: Issues the Request For Quotation, selects the Bidders, expedites the proposals, does the Commercial tabulation, asks for approvals, issues the Purchase Order, registers the Purchase Order in Procurement SQL system, detailing the items and sub-items of each P.O., for cost control purposes and expedites the deliveries, and distribute the P.O. to all the involved disciplines.

- Warehouse Manager: Signs the LMR once confirmed that the Material requested in not available in the warehouse, incorporates the Material into the system and to inform to Buyer when it arrives to site.

- Site Cost Control Manager:  Completes the cost control account number to which the cost of buying the LMR will be assigned and signs the LMR. Gives the Buyer the budget available to the Material included in the LMR, in case there is any.

- Site General Services and Administration Manager: Signs the LMR to provide the money when the LMR will be supplied from the “Site Office”.

- Technical Office Manager or designated Manager at SITE (if required): Starts the LMR, in order to define the Material needed to be bought. In case that the LMR is associated with a potential backcharge to a Vendor, he shall inform about this to the Project Procurement Manager, who will manage it in accordance with PR-27 ”Suppliers Backcharges Procedure”. In case that the LMR is associated with a potential backcharge to one Subcontrator, he shall inform about this to the Site Subcontract Administration Manager, who will manage it accordingly with the Subcontractor.

- Site General Services and Administration Manager:  is responsible of all Purchase Orders related to office consumables, such as: paper, drinking water, coffee, toilette paper, etc.

- Subcontract Administration Manager: to communicate to the Subcontractor the back charge, in case the LMR has to be back charged to a Subcontractor, to keep updated subcontract log with all the cost to be back charged.

- FIELD PROCUREMENT SERVICES

Field procurement services include, but are not limited to, the following:

- Issuing of the Request For Quotation according to the related Local Material Requisition, requested and prepared with all the needed technical documentation by the Requester.

- Preparation of CBA and Purchase Order.

- Follow up, reviews and solution of all field Purchase Orders queries.

- Keep track of all LMRs processes and having updated the LMR Log.

- Closing out all local Purchase Order files.

The Procurement organization will be based inside the Procurement Group in HO (Madrid, Spain) and will control all procurement activities including Field Procurement.

In general, the Procurement activities will be developed from HO (Madrid) with the assistance of the Local Office or Site General Services and Administration Manager, if needed. Field Procurement will be done only for urgent matters and for small amounts, and will be approved by several people, depending of the total value, but as minimum by Site Manager, PPM and PM, in this order.

Site Technical Office Manager shall ensure that all field procurements comply with CLIENT’s applicable specifications, standards and requirements. Field procurement Materials shall meet the project quality requirements.  All local purchases shall be done through a LMR.  Also, is in charge of keeping the LMRs Log updated and do its monthly distribution to Site Cost Control Manager, Project Procurement Manager and Project Manager.

The Field Procurement will be done by a Buyer, supported by the Site Technical Office Manager or designated Manager at Site for that particular purchase. This Buyer shall be part of the Procurement Department and should keep informed to the PPM about the entire purchase process. CONTRACTOR delegates to the Buyer the authority of Purchase Order issue, after being checked and approved according to the Procurement Cycle.

For purchases which total amount adds around on a figure of 1.500 $, can be done by the Site General Services and Administration Manager, but he shall always follow this procedure for LMR and Purchase Order issuance. For these cases, no CBA will be issued.

- FIELD PROCUREMENT PROCEDURE

Field purchasing will follow the following requirements:

- VENDOR scouting, qualification and selection.

- Negotiation and query solving.

- Purchase Order issue.

- Reception, identification, damage control and Material storage.

- Coordination with inspection activity along with QA/QC Manager and Vendor.

- Closing out all field Purchase Orders.

- Taking care of shortage of Materials.

- PROCUREMENT CYCLE

## FOR MATERIAL

Request For Quotation

- The Site Technical Office Manager or the designated Manager at Site for that particular purchase (in case the Site Technical Office Manager has not been assigned to the project yet)  shall issue the LMR, using the standard format MI-45 Local Material Requisition (LMR) Format. The Site Technical Office Manager is the one in charge of requesting the signature of everyone included in the LMR, General Services and Administration Manager, Warehouse Manager, Site Cost Control Manager and Site Manager. It is very important to nominate the requested Material with its item & sub-item to identify the Material for the whole process perfectly.

- Once the LMR is complete, the Site Technical Office Manager will email it to the Buyer with the PPM in copy, in order to start the Request For Quotation process. No purchase process will start if the LMR is not duly signed by everyone. The Buyer will be located in Madrid headquarters, in the local offices or at SITE, it will depend on the country and project.

- Buyer issues the Request For Quotation to at least three SUPPLIERS. Exceptionally, if the needed is a rerun or there is some type of limitation, Buyer will send the Request For Quotation to the assigned Supplier only, with the previous PM approval.

Technical Bid Validation

The Buyer shall be responsible of receiving from the Requester the technical validation of the bids received.

Commercial Bid Analysis (CBA)

- The technically valid bids shall be received by the Buyer who will be responsible for a comparison of their commercial terms.

- The Buyer shall prepare the Commercial Bid Analysis (CBA) including minimum 3 Suppliers and suggesting a possible successful bidder. This CBA will be done using the standard format MI-46 Commercial Bid Analysis (CBA) Format.

- The Buyer shall require to the Site Cost Control Manager to verify if there is a budget for the purchase.  If there is, it shall be included in CBA.

- The CBA must be approved and signed by Buyer, Site Manager, Project Procurement Manager and Project Manager.

- The CBA must be approved, through email, always attaching the LMR, by the following people:

- From 0 $ to 5.000 $: Site Manager + Project Manager + Procurement Department Manager

- From 5.000 $ to 20.000 $: Site Manager + Project Manager + Procurement Department Manager + Project Division Manager

- From 20.000 $ on: Site Manager + Project Manager + Procurement Department Manager + Project Division Manager + Chief Operating Officer

Purchase Order

- Once the CBA has been approved, the Buyer shall issue the Purchase Order and shall send it to Project Procurement Manager together with the LMR and CBA for their revision and approval.

- The Purchase Order is signed by the Procurement Department Manager and Project Manager.

- The Purchase Order duly signed is returned to the Buyer to award and proceed with the order.

- The Buyer shall include the Purchase Order in the procurement software classifying it as “Pedido de Obra”. Item / sub-item shall be perfectly identified.

- The Buyer shall distribute, or confirm that the P.O. is distributed, to all the involved disciplines, including Administration Department.

- In the case of Purchase Orders done by the General Services and Administration Manager (< 1,500.00 USD), they shall be signed by the Project Manager and Site Cost Control Manager must include them in the system in order to be  considered in the project cost control (see point 6.3).

Expediting

The delivery of the Materials purchased shall be monitored, expedited and controlled by the Buyer.

Material  Receiving Inspection

Once the Material arrives at Site, the Requester shall validate the compliance with the technical requirements requested through the LMR.

Invoicing

The invoices shall be sent by the Vendors to the office detailed in the Purchase Order, it can be a local office or headquarters. These invoices shall be introduced in the regular project invoice approval process.

## FOR LOCAL SERVICES

If any service is required at Site, the person in charge to prepare the Contracts or Purchase Orders for those services will be the Local Office representative if exist, if not the General Services and Administration Manager/ Site Manager shall be the responsible. .

For these cases, the local office representative shall always follow the procedure for LMR and Purchase Order issuance, specified in this procedure. CBA is required.

Once P.O is placed, the Local Office representative shall update LOCAL SERVICES PO log and send both, the PO and log, to the Site Cost Control Manager and General Services and Administration Manager in order to upload the new P.O in SQL software and accounting software, respectively.

## FOR SITE OFFICE MATERIAL

For purchases which total amount adds up to 1.500 $, the General Services and Administration Manager will be in charge for Purchase Order preparation, but he shall always follow the procedure for LMR and PURCHASE ORDER issuance, specified in this procedure.  For these cases, no CBA will be issued.

Once PO is placed, the General Services representative shall update SITE OFFICE MATERIAL PO log and send both, the PO and log, to Site Cost Control and Administrative department in order to upload the new PO in SQL software and accounting software, respectively.

For purchases which total amount higher than 1.500 $, the General Services´ representative at SITE will send the LMR to BUYER with PPM in copy and the clause 6.1 will be followed.

NEEDS / LOCAL PROCUREMENT

Attachment I – LOCAL PROCUREMENT FLOWCHART

SITE OFFICCE MATERIAL

> 1500 USD

< ó = 1500 USD

LOCAL SERVICES

LMR

Any amount

Any amount

LMR

MATERIAL

PO PROCUREMENT DEPARTMENT MADRID

CBA required

LMR

PO SITE GENERAL SERVICES

CBA not required

LMR

MADRID PROCUREMENT DEPARTMENT UPLOAD PO´s (NO ITEMS REQUIRED)

SITE COST CONTROL RESPONSIBLE UPLOAD PO´s IN THE SYSTEM (NO ITEMS REQUIRED)

MADRID PROCUREMENT DEPARTMENT UPLOAD PO´s AND ITEMS IN THE SYSTEM

SITE COST CONTROL RESPONSIBLE UPLOAD PO´s IN THE SYSTEM (NO ITEMS REQUIRED)

PO LOCAL OFFICE

(or General Services and Administration Manager/ Site Manager)

PO PROCUREMENT DEPARTMENT MADRID